## Sheet1
SI NO | User Story | Assigned To | Status | Estimated Date | Completion Date
1 | High Level Design | Guru | Completed | 2019-03-25 | 2019-03-25
|  | Ganesh | Completed | 2019-03-25 | 2019-03-25
2 | Create Directory Structure | Guru | In Progress | 2019-03-26
3 | Create Git Repository For Team | Ganesh | In Progress | 2019-03-26
4 | Identify Sprint tasks | Guru | In Progress | 2019-04-04
|  | Ganesh | In Progress | 2019-04-04